## Visual 3 to 21 December 2018
Feature | 12-Jan-19 | 13-Jan-19 | 14-Jan-19 | 15-Jan-19 | 16-Jan-19 | 17-Jan-19 | 18-Jan-19 | 19-Jan-19 | 20-Jan-19 | 21-Jan-19 | 22-Jan-19 | 23-Jan-19 | 24-Jan-19 | 25-Jan-19 | 26-Jan-19 | 27-Jan-19 | 28-Jan-19 | 29-Jan-19 | 30-Jan-19 | 31-Jan-19 | 01-Feb-19 | Impacted
FCO / Expiries | [12 empty] | EDM FCO |  |  |  |  | FX Expiry |  |  |  | Clearing Members Trading Members Information Subscribers
Volume | [6 empty] | Volume against CMs and TMs 40k on EDM 10k for FXM 800K for EQM | [13 empty] | Volume against CMs and TMs 40k on EDM 10k for FXM 800K for EQM | Clearing Members
JSE Web Margin & Option Calculator |  |  | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator |  |  | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator |  |  | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members to access and perform option and margin calcultion on JSE Web Calculator | Trading Members
Client & Trading Member Transfer |  |  |  | Member Transfers with branches Dummy TMs will be transferred across all CMs during couse of cycle. CMs to identify clients that may be transferred. Separate worksheet to be provided. |  | Member Transfers with branches Dummy TMs will be transferred across all CMs during couse of cycle. CMs to identify clients that may be transferred. Separate worksheet to be provided. |  |  |  |  | Client Transfers Dummy TMs will be transferred across all CMs during couse of cycle. CMs to identify clients that may be transferred. Separate worksheet to be provided. |  | Client Transfers Dummy TMs will be transferred across all CMs during couse of cycle. CMs to identify clients that may be transferred. Separate worksheet to be provided. |  |  |  |  | Client and Trading Member Transfers (Placeholder) Dummy TMs will be transferred across all CMs during couse of cycle. CMs to identify clients that may be transferred. Separate worksheet to be provided. |  | Client and Trading Member Transfers (Placeholder) Dummy TMs will be transferred across all CMs during couse of cycle. CMs to identify clients that may be transferred. Separate worksheet to be provided. |  | Clearing Members
Corporate Actions | [10 empty] | Cash Dividend On Local Equity (LDT Date) RD-23 | Cash Dividend On Local Equity (X Date) RD-23 | [5 empty] | Unbundling Local Equity (LDT Date) RD-12 | Unbundling Local Equity (Ex Date) RD-12 |  |  | Clearing Members Trading Members Information Subscribers
OBO Trade Reporting |  |  | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 |  |  | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 |  |  | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Trade Reports + Trade Cancellations CM-704 & CM-707 | Clearing Members Trading Members
Commissions |  |  | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. |  |  | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. |  |  | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Commissions Epic, with particular emphasis on balancing on commissions at EOD Clearing Members to ensure all commissions scenarios are tested. | Clearing Members Trading Members
JSE Booking Fees |  |  | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios |  |  | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios |  |  | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Fee Balancing - Clearing Members to focus on balancing of booking fees based on trade and commission scenarios | Clearing Members
Additional Margin |  |  |  | Apply additional margin CM-621 CMs to request if required | Remove additional margin CM-623 CMs to request if required | Apply additional margin CM-621 CMs to request if required | Remove additional margin CM-623 CMs to request if required |  |  |  | Apply additional margin CM-621 CMs to request if required | Remove additional margin CM-623 CMs to request if required | Apply additional margin CM-621 CMs to request if required | Remove additional margin CM-623 CMs to request if required |  |  |  | Apply additional margin CM-621 CMs to request if required | Remove additional margin CM-623 CMs to request if required | Apply additional margin CM-621 CMs to request if required | Remove additional margin CM-623 CMs to request if required | Clearing Members
JSE Risk Fees and Interest |  |  | STT will provide extract of daily risk fee and interest calculation results in build up to month end | STT will provide extract of daily risk fee and interest calculation results in build up to month end | STT will provide extract of daily risk fee and interest calculation results in build up to month end | STT will provide extract of daily risk fee and interest calculation results in build up to month end | STT will provide extract of daily risk fee and interest calculation results in build up to month end |  |  | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor |  |  | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor | CMs to provide extract of daily risk fee calculation results as provided by software vendor | Balancing on Risk and Interest fees - month end CM-145 | Clearing Members
Settlement Management |  |  | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 |  |  | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 |  |  | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 | Settlement Management & External Payment CM-130 & CM-134 Calculate the interest on ZAR cash collateral at the end of the month for a non-resident client CM-131 Calculate the interest on ZAR cash collateral on the last business day of the month. CM-400 Generate Settlement Instruction for ZAR at EOD - last business day of the Month CM-132 | Clearing Members
CM Fee Balancing (non-exchange fees) |  |  | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly |  |  | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly |  |  | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | CMs to verify fees to CM clients have calculated correctly | Clearing Members
CM Downstream accounting verification |  |  | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries |  |  | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries. CM to confirm for month end specifically. | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries |  |  | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries. CM to confirm for month end specifically. | CMs to confirm processing of accounting entries | CMs to confirm processing of accounting entries | Clearing Members
CM Downstream system verification |  |  | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems |  |  | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems |  |  | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | CMs to confirm processing in own downstream systems | Clearing Members
Scheduler |  |  | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working |  |  | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working |  |  | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | CMs to confirm scheduler working | Clearing Members
EOD Rerun | [12 empty] | EoD re-run at CM balancing 1 (Reason = Price) CM-651 |  |  |  |  | EoD re-run at CM balancing 1 (Reason = IMR CM-311 |  |  |  | Clearing Members
Client Reports |  |  | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports |  |  | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports |  |  | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | CMs to generate client reports | Clearing Members
TM Nutron Decommissiong Test |  |  | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment |  |  | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | Trading on REMAINING Nutron Markets in Decom environment | [7 empty] | Trading Members / Info Subscribers
FXM Market Making |  |  | Connectivity Testing confirmations and configurations Make prices on screen (Not Monitored) | Connectivity Testing confirmations and configurations Make prices on screen (Not Monitored) | Make prices on screen | Make prices on screen | Make prices on screen |  |  | Make prices on screen | Make prices on screen | Make prices on screen | Make prices on screen | Make prices on screen |  |  | Make prices on screen | Make prices on screen | Make prices on screen | Make prices on screen | Incentive Quaslification status checks for all categories (Capital Market/BI) Billing Summary (Capital Markets) | Market Makers