## Sheet1
JSE Integrated Trading and Clearing (ITaC) Project 1B: Test scenarios and Run Plan for MCMT Cycle 2
[7 empty] | Test Execution Feedback |  |  | Re-test Execution Feedback
No. | Epic | Feature | Business Scenario | Objective | To be executed by (JSE/Clearing Member) | Execution Cycle | Executed? (Y/N) | Pass / Fail / N/A | Fail Reason | Scenario Retested (Pass/Fail) | Fail Reason
1 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his House main account to a different TM’s Tripartite Client Main account and the Counterparty accepts the request | CM to action | Clearing Member | 2
2 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Client suspense account to a different TM's Tripartite Client Main Account and the counterparty TM accepts the request. | CM to action | Clearing Member | 2
3 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Sub account to a different TM's Tripartite Client Main Account and the counterparty TM accepts the request. | CM to action | Clearing Member | 2
4 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his House main account to a different Branch Tripartite Client Main account and the Counterparty accepts the request | CM to action | Clearing Member | 2
5 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Client suspense account to a different Branch Tripartite Client Main Account and the counterparty TM accepts the request. | CM to action | Clearing Member | 2
6 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Sub account to a different Branch Tripartite Client Main Account and the counterparty TM accepts the request. | CM to action | Clearing Member | 2
7 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch main account to a different TM's Tripartite Client main account and the counterparty TM accepts the request. | CM to action | Clearing Member | 2
8 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch Client suspense account to a different TM's Tripartite Client Main Account and the counterparty accepts the request. | CM to action | Clearing Member | 2
9 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch suspense account to a different TM's Tripartite Client main account and the counterparty TM accepts the request. | CM to action | Clearing Member | 2
10 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his House main account to a different Branch Tripartite Client Main account and the Counterparty Branch accepts the request | CM to action | Clearing Member | 2
11 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Client suspense account to a different Branch Tripartite Client Main Account and the counterparty Branch accepts the request. | CM to action | Clearing Member | 2
12 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Sub account to a different Branch Tripartite Client Main Account and the counterparty Branch accepts the request. | CM to action | Clearing Member | 2
13 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch main account to a different Branch Tripartite Client main account and the counterparty Branch accepts the request. | CM to action | Clearing Member | 2
14 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch Client suspense account to a different Branch Tripartite Client Main Account and the counterparty Branch accepts the request. | CM to action | Clearing Member | 2
15 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch suspense account to a different Branch Tripartite Client main account and the counterparty Branch accepts the request. | CM to action | Clearing Member | 2
16 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his House main account to a different TM’s Tripartite Client Main account and the Counterparty rejects the request | CM to action | Clearing Member | 2
17 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Client suspense account to a different TM's Tripartite Client Main Account and the counterparty TM rejects the request. | CM to action | Clearing Member | 2
18 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Sub account to a different TM's Tripartite Client Main Account and the counterparty TM rejects the request. | CM to action | Clearing Member | 2
19 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his House main account to a different Branch Tripartite Client Main account and the Counterparty rejects the request | CM to action | Clearing Member | 2
20 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Client suspense account to a different Branch Tripartite Client Main Account and the counterparty TM rejects the request. | CM to action | Clearing Member | 2
21 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Sub account to a different Branch Tripartite Client Main Account and the counterparty TM rejects the request. | CM to action | Clearing Member | 2
22 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch main account to a different TM's Tripartite Client main account and the counterparty TM rejects the request. | CM to action | Clearing Member | 2
23 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch Client suspense account to a different TM's Tripartite Client Main Account and the counterparty rejects the request. | CM to action | Clearing Member | 2
24 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch suspense account to a different TM's Tripartite Client main account and the counterparty TM rejects the request. | CM to action | Clearing Member | 2
25 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his House main account to a different Branch Tripartite Client Main account and the Counterparty Branch rejects the request | CM to action | Clearing Member | 2
26 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Client suspense account to a different Branch Tripartite Client Main Account and the counterparty Branch rejects the request. | CM to action | Clearing Member | 2
27 | Deal Management | Tripartite Trade Allocation | TM requests to allocate a tripartite trade from his Sub account to a different Branch Tripartite Client Main Account and the counterparty Branch rejects the request. | CM to action | Clearing Member | 2
28 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch main account to a different Branch Tripartite Client main account and the counterparty Branch rejects the request. | CM to action | Clearing Member | 2
29 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch Client suspense account to a different Branch Tripartite Client Main Account and the counterparty Branch rejects the request. | CM to action | Clearing Member | 2
30 | Deal Management | Tripartite Trade Allocation | TM Branch requests to allocate a tripartite trade from his Branch suspense account to a different Branch Tripartite Client main account and the counterparty Branch rejects the request. | CM to action | Clearing Member | 2
31 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his House Main Account to another TM | CM to action | Clearing Member | 2
32 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Client Suspense account to another TM | CM to action | Clearing Member | 2
33 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Sub account to another TM | CM to action | Clearing Member | 2
34 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Client Main to another TM | CM to action | Clearing Member | 2
35 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his House Main Account to another Branch | CM to action | Clearing Member | 2
36 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Client Suspense account to another Branch | CM to action | Clearing Member | 2
37 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Sub account to another Branch | CM to action | Clearing Member | 2
38 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Client Main to another Branch | CM to action | Clearing Member | 2
39 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his House Main Account to another Branch Client | CM to action | Clearing Member | 2
40 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Client Suspense account to another Branch Client | CM to action | Clearing Member | 2
41 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Sub account to another Branch Client | CM to action | Clearing Member | 2
42 | Deal Management | CM On Behalf of | TM to book an NT type Off Book Trade from his Client Main to another Branch Client | CM to action | Clearing Member | 2
43 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch House Main Account to another TM | CM to action | Clearing Member | 2
44 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch Client Suspense account to another TM | CM to action | Clearing Member | 2
45 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch Sub account to another TM | CM to action | Clearing Member | 2
46 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch Client Main to another TM | CM to action | Clearing Member | 2
47 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch House Main Account to another Branch | CM to action | Clearing Member | 2
48 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch Client Suspense account to another Branch | CM to action | Clearing Member | 2
49 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch Sub account to another Branch | CM to action | Clearing Member | 2
50 | Deal Management | CM On Behalf of | Branch to book an NT type Off Book Trade from his Branch Client Main to another Branch | CM to action | Clearing Member | 2
51 | Settlement Management | Commissions | Add commission - TM adds a new commission against a TM of another CM | CM to action | Clearing Member | 2
52 | Settlement Management | Commissions | Cancel commission against a TM | CM to action | Clearing Member | 2
53 | Settlement Management | Commissions | Add Commission - TM adds new commission against another TM | CM to action | Clearing Member | 2
54 | Settlement Management | Commissions | Reject commission against a TM | CM to action | Clearing Member | 2
55 | Settlement Management | Commissions | Add commission - CM adds new commission on behalf of a TM against another TM | CM to action | Clearing Member | 2
56 | Settlement Management | Commissions | Add commission - CH (JSE) adds a new commission on behalf of a TM against another TM | CM to action | Clearing Member | 2
57 | Settlement Management | Commissions | Cancel commission against a TM after the settlement instruction is created | CM to action | Clearing Member | 2
58 | Position Management | Manual Options Exercise and Abandon | Exercising of an EDM American Put Option before the cut-off time | CM to action | Clearing Member | 2
59 | Position Management | Manual Options Exercise and Abandon | Exercising of an EDM American Call Option before the cut-off time | CM to action | Clearing Member | 2
60 | Position Management | Manual Options Exercise and Abandon | Abandon of an EDM American Put Option before the cut-off time | CM to action | Clearing Member | 2
61 | Position Management | Manual Options Exercise and Abandon | Abandon of an EDM American Put Option before the cut-off time | CM to action | Clearing Member | 2
62 | Position Management | Position sub account modification | Perform position sub account modification from a TM house sub account to a TM House main account | CM to action | Clearing Member | 2
63 | Position Management | Position sub account modification | Perform position sub account modification from a TM house suspense account to a TM House main account | CM to action | Clearing Member | 2
64 | Position Management | Position sub account modification | Perform position sub account modification from a TM client suspense account to a TM House main account | CM to action | Clearing Member | 2
65 | Position Management | Position sub account modification | Perform position sub account modification from a TM client suspense account to a TM House sub account | CM to action | Clearing Member | 2
66 | Position Management | Position sub account modification | Perform position sub account modification from a TM house sub account to a TM House sub account | CM to action | Clearing Member | 2
67 | Position Management | Position sub account modification | Perform position sub account modification from a Branch house main account to a Branch House sub account | CM to action | Clearing Member | 2
68 | Position Management | Position sub account modification | Perform position sub account modification from a Branch client suspense account to a Branch House main account | CM to action | Clearing Member | 2
69 | Position Management | Position sub account modification | Perform position sub account modification from a Branch client suspense account to a Branch House sub account | CM to action | Clearing Member | 2
70 | Futures Close Out | Options Expiry on RTC | Auto Excercise Option at FCO: Put american option | CM to listen and verify | JSE | 2
71 | Futures Close Out | Options Expiry on RTC | Auto Exercise Option at FCO: Call american option | CM to listen and verify | JSE | 2
72 | Futures Close Out | Options Expiry on RTC | Auto Abandon Option at FCO: Call american option | CM to listen and verify | JSE | 2
73 | Futures Close Out | Options Expiry on RTC | Auto Abandon Option at FCO: Put American option | CM to listen and verify | JSE | 2
74 | Futures Close Out | Close out in RTC | Close out future on EDM with Settlement Type = Physical for Standard Expiry | CM to listen and verify | JSE | 2
75 | Futures Close Out | Close out in RTC | Close out future on EDM with Settlement Type = Cash for Standard Expiry | CM to listen and verify | JSE | 2
76 | Futures Close Out | EDM Futures Close Out | Publish Equity FCO prices | CM to listen and verify | JSE | 2
77 | Futures Close Out | Validation of VM at close Out | Mark -To-Market future | CM to action | Clearing Member | 2
78 | Futures Close Out | Validation of VM at close Out | OTM Put on a mark to market Future | CM to action | Clearing Member | 2
79 | Futures Close Out | Validation of VM at close Out | ITM Put on a mark to market future | CM to action | Clearing Member | 2
80 | Futures Close Out | Validation of VM at close Out | OTM Call on a mark to market future | CM to action | Clearing Member | 2
81 | Futures Close Out | Validation of VM at close Out | ITM Call for a mark to market future | CM to action | Clearing Member | 2
82 | Futures Close Out | Validation of VM at close Out | Mark to Model future | CM to action | Clearing Member | 2
83 | Futures Close Out | Validation of VM at close Out | OTM Call on a mark to model future | CM to action | Clearing Member | 2
84 | Futures Close Out | Validation of VM at close Out | ITM Call on a mark to model future | CM to action | Clearing Member | 2
85 | Futures Close Out | Validation of VM at close Out | OTM Put on a mark to model future | CM to action | Clearing Member | 2
86 | Futures Close Out | Validation of VM at close Out | ITM Put on a mark to model future | CM to action | Clearing Member | 2
Test Scenatios that can be retested from Cycle 1
[7 empty] | Test Execution Feedback |  |  | Re-test Execution Feedback
No. | Epic | Feature | Business Scenario | Objective | To be executed by (JSE/Clearing Member) | Execution Cycle | Executed? (Y/N) | Pass / Fail / N/A | Fail Reason | Scenario Retested (Pass/Fail) | Fail Reason
1 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House main account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. | CM to action | Clearing Member | 1
2 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House main account to a different TM's House main account, and the counterparty TM rejects the assign request. | CM to action | Clearing Member | 1
3 | Deal Management | Assign trade | TM requests a trade assign from his House suspense account to a different TM's Branch main account | CM to action | Clearing Member | 1
4 | Deal Management | Principle Correction | Correct trade allocation from Branch Client main account to Branch main account | CM to action | Clearing Member | 1
5 | Deal Management | Principle Correction | Correct trade allocation from Branch Client main account to Branch sub account | CM to action | Clearing Member | 1
6 | Deal Management | Trade sub account Modification | To move an existing trade from a House sub account to a House main account | CM to action | Clearing Member | 1
7 | Deal Management | Trade sub account Modification | To move an existing trade from Client suspense account to House main account | CM to action | Clearing Member | 1
8 | Deal Management | Accumulate trades | Accumulate trades - Member Client Accounts | CM to action | Clearing Member | 1
9 | Deal Management | Accumulate trades | Accumulate - TM house accounts | CM to action | Clearing Member | 1
10 | Deal Management | Trade sub account Modification | To move an existing trade from Client suspense account to House sub account | CM to action | Clearing Member | 1
11 | Deal Management | Accumulate trades | Accumulate trades - Member Client accounts; Add additional Trade | CM to action | Clearing Member | 1
12 | Deal Management | Accumulate trades | Accumulate trades - Member client accounts; Add additional trade | CM to action | Clearing Member | 1
13 | Deal Management | Allocation correction | Correct trade allocation from Branch Client main account to another Branch Client main account | CM to action | Clearing Member | 1
14 | Deal Management | Assign trade | TM Branch requests a trade assign (give-up) from his Branch main account to a different TM's Branch main account, and the counterparty TM Branch accepts (take-up) the assign request. | CM to action | Clearing Member | 1
15 | Deal Management | Assign trade | TM Branch requests a trade assign (give-up) from his Branch sub account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. | CM to action | Clearing Member | 1
16 | Deal Management | Assign trade | TM Branch requests a trade assign (give-up) from his Branch Client suspense account to a different TM's Branch main account, and the counterparty TM Branch accepts (take-up) the assign request. | CM to action | Clearing Member | 1
17 | Deal Management | Trade sub account Modification | To move an existing trade from Branch sub account to Branch main account | CM to action | Clearing Member | 1
18 | Deal Management | Accumulate trades | Accumulate trades - Branch client accounts | CM to action | Clearing Member | 1
19 | Deal Management | Accumulate trades | Accumulate two accumulated trades to determine an average price | CM to action | Clearing Member | 1
20 | Deal Management | Accumulate trades | Accumulate - Branch house accounts | CM to action | Clearing Member | 1
21 | Deal Management | Accumulate trades | Accumulate and then Assign allowed account types: From House main to Branch main: | CM to action | Clearing Member | 1
22 | Deal Management | Allocate Trade | To allocate a trade from a House main account to multiple Client main accounts | CM to action | Clearing Member | 1
23 | Deal Management | Allocate Trade | To allocate a trade from a House suspense account to multiple Client main accounts | CM to action | Clearing Member | 1
24 | Deal Management | Allocate Trade | To allocate a trade from a House sub account to multiple Client main accounts | CM to action | Clearing Member | 1
25 | Deal Management | Trade sub account Modification | To move an existing trade from a House main account to a Client suspense account | CM to action | Clearing Member | 1
26 | Deal Management | Allocation correction | Correct trade allocation from Client main account to another Client main account | CM to action | Clearing Member | 1
27 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his Client suspense account to a different TM's Branch main account, and the counterparty TM Branch accepts (take-up) the assign request. | CM to action | Clearing Member | 1
28 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House main account to a different TM's House main and Branch Main accounts, and the counterparty TMs accept (take-up) the assign request. | CM to action | Clearing Member | 1
29 | Deal Management | Trade sub account Modification | To move an existing trade from Branch main account to Branch Client suspense account | CM to action | Clearing Member | 1
30 | Deal Management | Assign trade | TM Branch requests a trade assign (give-up) from his Branch Client suspense account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. | CM to action | Clearing Member | 1
31 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House main account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. The give-up trade is partially reserved as a result of a previous assign | CM to action | Clearing Member | 1
32 | Deal Management | Trade sub account Modification | To move an existing trade from Branch sub account to Branch Client suspense account | CM to action | Clearing Member | 1
33 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House main account to a different TM's House main account, and then cancels the request before it is accepted. | CM to action | Clearing Member | 1
34 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his Branch main account to a different Branch House main account, and then cancels the request before it is accepted. | CM to action | Clearing Member | 1
35 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House sub account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. | CM to action | Clearing Member | 1
36 | Deal Management | Assign trade | TM Branch requests a trade assign (give-up) from his Branch sub account to a different TM's Branch main account, and the counterparty TM Branch accepts (take-up) the assign request. | CM to action | Clearing Member | 1
37 | Deal Management | Trade sub account Modification | To move an existing trade from a House sub account to a different House sub account | CM to action | Clearing Member | 1
38 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his Client suspense account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. | CM to action | Clearing Member | 1
39 | Deal Management | Assign trade | TM Branch request a trade assign (give-up) from his Branch main account to a different TM's House main account, and the counterparty TM accepts (take-up) the assign request. | CM to action | Clearing Member | 1
40 | Deal Management | Principle Correction | Correct trade allocation from Client main account to House main account | CM to action | Clearing Member | 1
41 | Deal Management | Principle Correction | Correct trade allocation from Client main account to House sub account | CM to action | Clearing Member | 1
42 | Deal Management | Trade sub account Modification | To move an existing trade from a House sub account to a Client suspense account | CM to action | Clearing Member | 1
43 | Deal Management | Trade sub account Modification | To move an existing trade from Branch sub account to another Branch sub account | CM to action | Clearing Member | 1
44 | Deal Management | Assign trade | TM requests a trade assign (give-up) from his House main account to a different TM's Branch main account, and the counterparty TM Branch rejects the assign request. | CM to action | Clearing Member | 1
45 | Settlement Management | CM Balancing | CM Balancing 1 (part of EOD process) | CM to action | Clearing Member | 1
46 | Settlement Management | CM Balancing | CM Balancing 2 (part of EOD process) | CM to action | Clearing Member | 1